## Slide 1: Steering Committee June 3rd-4th, 2020
Coordination: Latifa Abdennebi-Najar
Project Manager: Florence Macherez
IDELE
The PRIMA programme is supported under Horizon 2020, the European Union’s Framework Programme for Research and Innovation
http://www.milkqua.eu
Section 2. Multi-topic-2018
Topic of the call:
1.3.2: Food Safety in Local Chains

## Slide 2: WP1-Coordination and management
Short overview of the project, updates
State of implementation

## Slide 3
PARTNERS
France (Idele, INRA)
Italy (UMIL)
Spain (CISC)
Portugal (UPFF)
Tunisia : (OEP, LPAM, ENMV, INAT, Delice Danone)

## Slide 4: PROJECT TIMELINE & MEETINGS
Reporting Period 1
Reporting Period 2
Launch
Meeting
Starting date
April 1st 2019
M1 M6 M12
M18 M24 M30 M36
1st Annual Meeting
& Project Steering Board
3rd annual
Meeting & Project Steering Board
Report 1
October 2020
Final Report
End of the Project
Consortium Agreement
2nd annual
Meeting
& Project Steering Board
April 1st 2021
April 1st 2022
April 1st 2020
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Project Executive Committee meetings (once a month)
Delayed

## Slide 5: …and invitees
Organisation | Representative
IDELE | Latifa Abdennebi-Najar
INRAE | Saïd Bouhallab
CSIC | Sonia Andrés
UMIL | Fabrizio Ceciliani
UPFF | David Pereira
INRAT | Hichem Bensalem
LPAM | Riadh Ksouri /Ibtissem Hamrouni
ENMV | Monia Daaloul
OEP | Henda Hanafi
DELICE DANONE | Mohammed Ali Touzri
STEERING BOARD COMPOSITION
At least one representative from partner organisations…

## Slide 6
Ultimate Goal
Decreasing milk-associated health hazards, by reducing the use of conventional antimicrobial products in Tunisian dairy farms to align with the concept of One Health
Notes: milk safety and quality are critical issues for human health and welfare

## Slide 7
OBJECTIVES
Objective 1: Implementing an extension-based national milk program (QMP) to reduce the incidence of mastitis and the consequent use of antibiotics in Tunisia, improve animal welfare and the sustainability of milk production system all along the dairy chain in Tunisia (WP2, IDELE, OEP, ENMV, Danone Delice) (Leaders : Philippe Roussel & Benedicte Fusai (Idele), with the great help of Henda Hanafi!)

## Slide 8
OBJECTIVES
Objective 2: Exploring the potential use of essential oils and Tunisian plant extracts with antibacterial activities on the udder and in diets (In vitro and In vivo studies) of both young and adult dairy cattle and their impact on milk quality (Technological studies) and acceptability (consumer studies) (WP3, WP4, WP5, WP6, WP7: UPFF, LPAM, CSIC, INRAe, IDELE, ENMV, INRAT (leader: David Pereira, contributors: Sonia Andres, Fabrizio Ceciliani, Said Bouhallab, Ibtissem Hamrouni & Raja Serairi )

## Slide 9
Expected impacts
Develop new procedures for qualifying and classifying production sites and zoning from North West to South Tunisia
Develop and validate bio-based protection practices, to select and characterize the natural extracts and species with protective characteristics for food production, quality and storage
Increase the awareness of the consumer and contribute to a decrease of antibiotics use and of mastitis prevalence
Facilitate the development of new norms and standard for hazards prediction and risk assessment
NORMS AND STANDARDS
IMPROVEMENT OF AGRICULTURE SYSTEM & SUSTAINABLE MANAGEMENT OF AGRICULTURE RESOURCES

## Slide 10: Organization and progression (1)
Renato Pereira
Post-Doc, hired Jan 2020 (WP3)
Ralph Nehme (PhD, WP4)

## Slide 11: Organization and progression (2)
WP/partner | M-M | Idele | CSIC | INRAe | UPFF | LPAF | LPAM | UMIL | OEP
WP2 - Innovative QMP Practices in Tunisia | M1-34 | X |  |  |  |  |  |  | X
WP3 - In Vitro Evaluation of Bioactive Molecules and Extracts | M1-18 |  | X |  | X |  | X |  | 
WP4 - In Vivo Evaluation of Bioactive Molecules and Extracts | M1-32 | X | X |  |  | X |  |  | 
WP5 - System Biology Assessment of the Effects of EO after In Vitro and In Vivo Studies | M19-32 | X | X |  |  |  |  | X | 
WP6 - Milk and Dairy Products Processing and Consumer Studies | M12-30 | X |  | X |  |  | X |  | 
WP7 - Consumer Assessment of Milk | M11-30 |  |  |  |  |  |  |  | 
IN PROGRESS
DELAYED!
DELAYED!
DELAYED!
ON TIME
DELAYED!

## Slide 12: PRIMA-IS portal = Smartsheet
All partners have access to the SmartSheet tool on the PRIMA-IS portal that includes a deliverable sheet, a technical sheet and a budget sheet
FINANCIAL - TECHNICAL MONITORING AND REPORTING

## Slide 13
Thank you for your attention