## Slide 1: WP 4: In vivo evaluation of bioactive molecules and extracts
WPL: Sonia Andres, CSIC, Spain
MilkQua Project Steering Board, June 3rd, 2020
The PRIMA programme is supported under Horizon 2020, the European Union’s Framework Programme for Research and Innovation

## Slide 2: Work Package 4
Introduction to the scientific approach
Activities and outcomes for first and second years
Short presentation of Ralph Nehme’s (PhD) background
Discussion

## Slide 3: Essential oils, promising alternatives to antibiotics in livestock
Antimicrobials (e.g., membrane damage, disruption of quorum sensing)
Anti-inflammatory properties at intestinal level ( e.g., NF-kβ and Nrf2)
Antioxidative properties
Estimulation of digestive secretions for improving nutrient digestibility
Introduction to the scientific approach
Inconsistent results in the literature due to several reasons
It is fundamental a better characterization of EOs
In MilkQua WP4 (in vivo studies) will progress on the basis of previous results (e.g., WP3)
But:

## Slide 4: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
FEED EFFICIENCY AND HEALTH STATUS of dairy cattle being fed EOs (T4.2)
EOs as a curative solution applied directly on the udder with MASTITIS (T4.3 and T4.4)
Activities and outcomes for first and second years

## Slide 5: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
Activities and outcomes for first and second years

## Slide 6: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
Activities and outcomes for first and second years
Deliverable 4.1. (CSIC, M10). DELAYED
Pending some minor details of some experiments [IDELE, ENMV and LPAF (INRAT)]
READY for being submitted to PRIMA in September

## Slide 7: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
FEED EFFICIENCY AND HEALTH STATUS of dairy cattle being fed EOs (T4.2)
Activities and outcomes for first and second years
Sub-task 4.2.1. Feed efficiency and health status during the replacement period of dairy calves supplied with EOs along the first two months of life (CSIC)
EOs
Feed efficiency and health
CTRL vs DOHaD group
Birth 12 M
Newborn dairy calves
Deliverables 4.2 and 4.3. (CSIC, M24). DELAYED between 6 and 12 months
Trial to be started in September 2020 (pending of Covid-19 evolution)
Four sampling times along 12 months (feaces and plasma) to be submitted to UNIMI (-omics)

## Slide 8: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
FEED EFFICIENCY AND HEALTH STATUS of dairy cattle being fed EOs (T4.2)
Activities and outcomes for first and second years
Sub-task 4.2.1. Feed efficiency and health status during the replacement period of dairy calves supplied with EOs along the first two months of life (CSIC)
Sub-task 4.2.2. Sub-task 4.2.2. Feed efficiency, milk yield and quality and health status of adult dairy cattle supplied with EOs during the mid-lactation [LPAF (INRAT)]
EOs
Feed efficiency and health
Mid-lactation
CTRL vs EO group
2×2 design
Adult dairy cows
Deliverables 4.4 (LPAF, M24) ON TIME, no delays
No samples to be shifted to other WPs.

## Slide 9: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
FEED EFFICIENCY AND HEALTH STATUS of dairy cattle being fed EOs (T4.2)
EOs as a curative solution applied directly on the udder with MASTITIS (T4.3 and T4.4)
Activities and outcomes for first and second years
Task 4.3. Mastitis under controlled conditions (CSIC and IDELE)
CONTROL vs.
EOs
1. Experimental farm (CSIC) (Bacterial count, SCC)
Adult dairy sheep
Preliminary study to test the safety and efficacy of EOs when applied intrammamary with DMSO
To be started the 21st of June 2020, final results by the end of July 2020
IMPORTANT: Dose to be tested (MIC? Higher than MIC?)
We can provide samples (milk, plasma) for other WPs, if needed (-omics, milk quality….)

## Slide 10: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
FEED EFFICIENCY AND HEALTH STATUS of dairy cattle being fed EOs (T4.2)
EOs as a curative solution applied directly on the udder with MASTITIS (T4.3 and T4.4)
Activities and outcomes for first and second years
Task 4.3. Mastitis under controlled conditions (CSIC and IDELE)
1. Experimental farm (CSIC) (Bacterial count, SCC)
2. Experimental farm (INRA) (Pathogenes, SCC)
CONTROL
EOs
AB
EOs+AB
Adult dairy cows
To be started in September 2020, final results by the end of October 2020 . DELAY of 6 months
IMPORTANT: Dose to be tested (MIC? Higher than MIC?)
Samples (milk, plasma) will be shifted for other WPs.

## Slide 11: List of tasks in WP4
Standardization of PROTOCOLS (T4.1)
FEED EFFICIENCY AND HEALTH STATUS of dairy cattle being fed EOs (T4.2)
EOs as a curative solution applied directly on the udder with MASTITIS (T4.3 and T4.4)
Activities and outcomes for first and second years
Task 4.3. Mastitis under controlled conditions (CSIC and IDELE)
Task 4.4. Mastitis, large scale study in Tunisian farms (ENMV)
CONTROL
EOs
AB
EOs+AB
1. Large scale study (Pathogens, SCC)
Adult dairy cows
To be started in…………. DELAY of 6 months??
Milk samples to be shifted to WP7.

## Slide 12: Ralph Nehme
Short presentation of Ralph Nehme’s (PhD) background
Joint PhDs (INRA, Idele)
INRAE´s validation on administrative documents . ARNT is the complement financial institution for the PhD. (the first request of funding was rejected due to insufficient information and we resubmit the demand on may April 2020, ).
Ralph can join Sonia and María José Ranilla in León to contribute to in vitro fermentation (probably in October depending on Covid-19 evolution). He will be co-author of the paper published.

## Slide 13: Points to be discussed
Discussion
Deliverable 4.1. Pending some minor details of some experiments [IDELE, ENMV and LPAF (INRAT)]
Progression of sub-task 4.4. [LPAF (INRAT)] One or two EOs to be tested?
Experimental design of dairy sheep experiment mastitis), dose, samples for other WPs, any other issue…
Any other concern…..