## Slide 1: Steering Board meeting June 3rd-4th 2020 Conclusions
Leader: Idele, Latifa Najar (coordinator) Florence Macherez (project manager)
The PRIMA programme is supported under Horizon 2020, the European Union’s Framework Programme for Research and Innovation

## Slide 2: Main conclusions and pending questions?
WP1 - Project Coordination and management
WP1
Need more scientific discussions between partners within WPs and between WPs
Covid-19 delays concerning all WPs
Interaction between WPs…
Sharing Deliverables with the whole consortium (Project Steering Board members) (eg. D3.1, D3.2 – LPAM)
WP2
Go further on analysis of strains in WP2
Focus on farms with less than 20 cows?
Stakeholders’ expectations regarding MilkQua
Danone’s position in the project
Slight delay of 1-1.5 month

## Slide 3: Main conclusions and pending questions?
WP1 - Project Coordination and management
WP3
Feasibility of using cow macrophages?
Extension of the toxicity studies on other models (rodent,…)
Stability of plants and EOs samples over time -> recommendation to store samples -20°C
Doses to be used
WP4
Molecules sent to Spain by LPAM: Riadh will organize rapid shipping (3 days delay)
Hichem will send the regime to Sonia
Lab will restart in Sept. Oct.
WP4 will postpone in vitro studies

## Slide 4: Main conclusions and pending questions?
WP1 - Project Coordination and management
WP5
Linking with another PRIMA project dealing with OMICS
Needs many scientific sharings with partners
WP6
Need much more communication between partners / consumer studies
Analysis of essential oils (cooperation with David)
Interact with Sergine (INRAE)
WP7
Studies in Tunisia and France… need to share methodologies

## Slide 5: Main conclusions and pending questions?
WP1 - Project Coordination and management
WP8
Need discussions during the Project Executive Committee about dissemination of deliverables and exploitation of results -> publishing deliverables on the website
Partners will publish articles about MilkQua on their institution’s website
Partners will retwit messages from MIlkQua Twitter and LinkedIn accounts
Idele, OEP, LPAM will translate flyers in French, Arabic
Ideas of events/meetings, opportunities for communication activities
Partners will help create articles and disseminate the Newsletter, website, social media

## Slide 6: Pending Questions
WP1 - Project Coordination and management

## Slide 7: Deliverables status Year 1 and 2
WP1 - Project Coordination and management

## Slide 8: Deliverables status Year 1 and 2
WP1 - Project Coordination and management

## Slide 9: Next steps
Next MilkQua Steering Board in Tunisia?
WP1 - Project Coordination and management

## Slide 10: Next steps
…..
WP1 - Project Coordination and management

## Slide 11: Next steps
…..
WP1 - Project Coordination and management

## Slide 12
Reporting Period 1
Reporting Period 2
Launch
Meeting
April 1st 2019
M1 M6 M12
M18 M24 M30 M36
1st Annual Meeting
& Project Steering Board
3rd annual
Meeting & Project Steering Board
Mid-term Report
Final Report
End of the Project
Consortium Agreement
2nd annual
Meeting
& Project Steering Board
April 1st 2021
March 31st 2022
April 1st 2020
Launch of the project
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
Stakeholder Meeting
+ Once a month: Project Executive Committee meetings
Project timing and reporting
WP1 - Project Coordination and management
Notes: The Project Steering Board as the ultimate decision-making body of the Consortium concerning the project strategy, the budget and costs issues, the dissemination, advises on exploitation and IPR as well as the legally binding actions. The Project Steering Board (PSB) is organised and chaired by the PCO and involves one representative for each Beneficiary.
Each Party shall have one representative and vote in the Project Steering Board. Decisions of the Project Steering Board are taken by simple majority of the votes.

## Slide 13
It will be prepared by the coordinator and the beneficiaries:
Explanation of the work carried out, on the use of ressources
Overview of the progress
If relevant, explanations on reasons for deviations, consequences, proposed corrective actions
Summary for publication
Deliverables and milestones
Dissemination, list of communication actions, capacity building
Contribution to operational objectives of Prima
Once validated, it will be submitted on-line by the Coordinator on the SmartSheet tool through the PRIMA-IS portal: deliverable sheet, a technical sheet and a budget sheet
Project reporting (M18 – October 2020)
WP1 - Project Coordination and management