# Roadmap of the communication-dissemination-exploitation activities

Table 5: General Roadmap of the MilkQua project

| Action | Date/Frequency | Objectives | Target audience | Mean | Responsible (participating partners) | Expected results |
| --- | --- | --- | --- | --- | --- | --- |
| All along the project |  |  |  |  |  |  |
| Feed MilkQua website and Social Media (Twitter and LinkedIn) | M1 - April 2019 to M36 - March 2022 If possible, a post per week | Make the project and its outcomes be known | Research community Industries and SME Civil society/Policy makers/EC | News and articles about events, results or any other material and information | ABSISKEY (all partners) | Website and Social Media statistics show increasing visits |
| MilkQua Communication and Dissemination Committee meetings | M1 - April 2019 to M36 - March 2022, monthly | Plan and monitor Communication and dissemination activities | Project partners | Communication and dissemination monitoring sheet | IDELE (ABSISKEY, all partners) | Timely targeted communication and dissemination activities |
| MilkQua Various stakeholders consultations (WP2) | M1 – April 2019 – M36 March 2022 | Consultations of | Tunisian project partners, Idele, end-users: Farmers organisations, industries and SMEs/ Policy makers |  | OEP (Idele, INRAT, ENMV, LPAM, Délice Danone) |  |
| Year 1 |  |  |  |  |  |  |
| MilkQua Twitter account creation | M1 – April 2019 | Make the project known | Research community Industries and SME Civil society/Policy makers/EC | Twits about launch event and project activities | IDELE | Information about MilkQua launch |
| MilkQua Kick Off meeting | M1 – April 2019 | Preparing project activities | Project partners | Meeting Article on the website and social networks | IDELE (all partners) | Build incentive among partners, inform about project launch |
| Establishment of the MilkQua Communication and Dissemination Committee meetings | M2 – May 2019 | Plan and monitor Communication and dissemination activities | Project partners | Communication and dissemination monitoring sheet | IDELE, ABSISKEY (all partners) | Timely targeted communication and dissemination activities |
| PRIMA Kick-Off Meeting | M3 – June 2019 | Make the project known | Research community Industries and SME Civil society/Policy makers/EC | Presentation PPT Article in PRIMA brochure | IDELE | Information about MilkQua in the EU and Mediterranean area |
| MilkQua Scientific Poster | M3 – June 2019 | Make the project known | Research community Industries and SME | 3rd International Symposium “Milk, vector of development”, Dakar, Senegal | IDELE, INRAE | Raise awareness about the project |
| 3rd International Symposium “Milk, vector of development”, Dakar, Senegal https://colloque.inra.fr/lait2019/ | M3 – June 2019 | Make the project known | International Research community Industries and SMEs | Scientific Poster, abstract, Participation to event | INRAE, IDELE | Raise awareness about the project |
| MilkQua LinkedIn account creation | M4 - July 2019 | Make the project known | Research community Industries and SME Civil society/Policy makers/EC | News and articles about project launch and planned activities | ABSISKEY | Information about MilkQua launch |
| MilkQua logo creation and validation | M4 – July 2019 | Project branding | Research community Industries and SME Civil society/Policy makers/EC | MilkQua project logo | ABSISKEY (all partners) | Project branding |
| IDELE Innovations Comice 2019 link | M9 - December 2019 | Make the project known | Research community Industries and SME Policy makers | Introduction to MilkQua: stand, scientific poster and first video | IDELE (UMIL, INRAE) | Around 180 participants Raise awareness about the project in France |
| 1st MilkQua Video (pilot) | M9 - December 2019 | Make the project known | Civil society/Policy makers/EC | Presented during IDELE Innovations Comice 2019 | ABSISKEY (all partners) | Raise awareness about the project in France |
| MilkQua Scientific Poster | M9 – December 2019 | Make the project known | Research community Industries and SMEs Policy makers | IDELE Innovations Comice 2019 | IDELE, INRAE | Raise awareness about the project in France |
| Publication of MilkQua Website | M10 – January 2020 | Central point for MilkQua communication activities and publications | Research community Industries and SMEs/ Civil society/ Policy makers/EC | Website, Social Networks | ABSISKEY (all partners) | Raising awareness on MilkQua project, partners, WPs, news, events… |
| MilkQua Project Dissemination and communication plan | M12 – April 2020 | Plan communication and dissemination activities | Project partners/Policy makers/EC | Project deliverable | IDELE, ABSISKEY (all partners) | Timely targeted communication and dissemination activities |
| Action | Date/Frequency | Objectives | Target audience | Mean | Responsible (participating partners) | Expected results |
| Year 2 |  |  |  |  |  |  |
| Mention of MilkQua project on partners’ websites | M12 – April 2020 to M18 - October 2020 Reminder if necessary | Make MilkQua known | Research community Industries and SMEs | Partners’ websites | ABSISKEY (all partners) | Link to the MilkQua project on each partner’s website |
| MilkQua Project visual identity, Templates for powerpoint presentations and word documents (reports and deliverables) | M12 – April 2020 | Branding | Research community Industries and SMEs/ Civil society/ Policy makers | Conferences, reports | ABSISKEY |  |
| 1st MilkQua Project Steering Board (remote) | M14 – 3rd – 4th June 2020 | Exchange of views between partners and Tunisian stakeholders | Project partners, Tunisian stakeholders (industries and academia) | Website, Social Networks | IDELE | Build incentive among partners, updates on project actions |
| 1st MilkQua Newsletter design and First issue of Newsletter in English, French, Arabic | M14 – June 2020 | Inform about project activities and advancements, first results | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks | ABSISKEY (all partners) | Raise awareness about the project and its scientific activities |
| 1st MilkQua Flyer in French and English, template for translation in Arabic | M15 – July 2020 | Make the project known | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks, Events | ABSISKEY (all partners) | Raises awareness about the project |
| Second MilkQua Scientific Poster | M15 – July 2020 | Make the project known | Research community Industries and SMEs | Scientific Conferences | ABSISKEY (Idele) | Raise awareness about the project and its scientific activities |
| 1st MilkQua video presenting the project (finalising) | M17 - September 2020 | Make the project known | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks, Events | ABSISKEY (all partners) | Website and Social Media statistics: increasing visits Raise awareness about the project |
| WBC World Buiatrics congress 2020 http://buiatrics.com/congresses/ | M18 – Oct. 2020 | Make the project known | Research community Industries and SMEs | Flyers, website, social media | CSIC | Meetings during scientific congress, Website and Social Media visits |
| 2nd issue of MilkQua Newsletter in English, French, Arabic | M19 – Nov. 2020 | Inform about project activities and advancements, first results | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks | ABSISKEY (all partners) | Raise awareness about the project and its scientific activities |
| EAAP European Association for Animal Production Annual Meeting (remote) https://eaap2020.org/ | M20 – December 2020 | Exchanges between partners, distribution of flyers | Research community Industries and SMEs | Website, social media | IDELE, INRAE, UMIL, CSIC | Meetings during scientific congress, Website and Social Media visits |
| Rencontres autour des Recherches sur les Ruminants Scientific congress, Paris, France http://journees3r.fr/spip.php?article4722 | M20 – December 2020 | Make the project known | Research community Industries and SMEs | Scientific poster, Flyers, website, social media | IDELE, INRAE | Meetings during scientific congress, views of the poster, flyer, Website and Social Media visits |
| 3rd issue of MilkQua Newsletter in English, French, Arabic | M22 – Feb. 2021 | Inform about project activities and advancements, first results | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks | ABSISKEY (all partners) | Raise awareness about the project and its scientific activities |
| Year 3 |  |  |  |  |  |  |
| MilkQua Project Steering Board, Tunis, Tunisia | M24 or M26 – 3rd April or June 2021 | Exchange of views between partners and Tunisian stakeholders | Project partners, Tunisian stakeholders (industries and academia) | Presentations, speeches, Website, Social Networks | IDELE and all partners | Share updates among partners, updates on project actions |
| 4th International Symposium “Milk, vector of development” (CIRAD-INRA-IDELE-OEP), Tunisia | M25 - May 2021 |  |  | Scientific poster, Flyers, website, social media | INRAE, IDELE, OEP |  |
| 4th issue of MilkQua Newsletter in English, French, Arabic | M25 –May 2021 | Inform about project activities and advancements, first results | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks | ABSISKEY (all partners) | Raise awareness about the project and its scientific activities |
| EAAP European Association for Animal Production Annual Meeting, Davos, Switzerland https://www.eaap2021.org/ | M28 - Aug. 31-Sept. 4th 2021 | MilkQua Scientific session (2 hours) Exchanges between partners, distribution of flyers | Research community Industries and SMEs | Powerpoint presentation and speech during a scientific session, Flyers, website, social media | IDELE, INRAE, UMIL, CSIC | Meetings during scientific congress, views of the Flyer, Website and Social Media visits |
| 2nd MilkQua video presenting some results | M30 – March 2021 | Make the project be known | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks, Events | ABSISKEY | Website and Social Media statistics: increasing visits Raise awareness about the project |
| WBC World Buiatrics congress 2021 http://buiatrics.com/congresses/ | M30 – Oct. 2021 | Make the project be known | Research community Industries and SMEs | Flyers, website, social media | CSIC | Meetings during scientific congress, Website and Social Media visits |
| 5th issue of MilkQua Newsletter in English, French, Arabic | M30 – Oct. 2021 | Inform about project activities and advancements, first results | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks | ABSISKEY (all partners) | Raise awareness about the project and its scientific activities |
| MilkQua Closing conference and last Project Steering Board | M36 – March 2022 | Exchange of views between partners and Tunisian stakeholders | Project partners, Tunisian stakeholders (industries and academia) | Presentations, speeches, Website, Social Networks | IDELE | Updates on project actions and results Website and Social Media visits |
| 6th issue of MilkQua Newsletter in English, French, Arabic | M36 – March 2022 | Inform about project activities and advancements, first results | Research community Industries and SMEs Civil society/Policy makers/EC | Website, Social Networks | ABSISKEY (all partners) | Raise awareness about the project and its scientific activities |
| Rencontres autour des Recherches sur les Ruminants Scientific congress, Paris, France http://journees3r.fr/spip.php?article4722 | M ?? – December 2022 | Make the project be known | Research community Industries and SMEs | Scientific poster, Flyers, website, social media | IDELE, INRAE | Meetings during scientific congress, views of the poster, flyer, Website and Social Media visits |