Second Project Steering Board Meeting

June 3rd-4th, 2020 – from 14.00-17.00/16.30

Remote Meeting

Agenda

Participants

| Organisation | Representative | Quality | E-mail |
| --- | --- | --- | --- |
| IDELE | Latifa Najar | Project coordinator, PSB member | Latifa.najar@idele.fr |
| INRAE | Saïd Bouhallab Sergine Even | WP6 leader, PSB member Invitee | said.bouhallab@inra.fr Sergine.even@inrae.fr |
| CSIC | Sonia Andrés Maria Josia Ranilla | WP4 leader, PSB member Invitee | sonia.andres@eae.csic.es mjrang@unileon.es |
| UMIL | Fabrizio Ceciliani Chiara Mariani | WP5 leader, PSB member | fabrizio.ceciliani@unimi.it chiara.mariani@unimi.it |
| UPFF | David Pereira Renato Pereira | WP3 leader, PSB member Invitee | dpereira@ff.up.pt ren.pereira@gmail.com |
| LPAM | Ibtissem Hamrouni Riadh Ksouri Raja SERAIRI Falleh Hanen | PSB member WP7 leader Represents the WP7 leader Invitee | ibtissem_hfr@yahoo.fr ksouririadh@gmail.com raja_serairi@yahoo.fr hanenfalleh@gmail.com |
| IDELE | Bénédicte Fusai Philippe Roussel Florence Macherez Djamila Meliani Valérie Hardit Faustine Noël Amandine Menet Ralph Nehme | WP2 leaders Project manager Assistant Invitee Invitee Invitee PhD student WP4 | Benedicte.fusai@idele.fr Philippe.roussel@idele.fr Florence.macherez@idele.fr Djamila.meliani@idele.fr Valerie.hardit@idele.fr Faustine.noel@idele.fr Amandine.menet@idele.fr ralphnehme95@gmail.com |
| INRAT | Hichem Bensalem | PSB member | bensalem.hichem@iresa.agrinet.tn |
| ENMV | Monia Daaloul | PSB member | moniajd2017@gmail.com |
| OEP | Henda Hanafi | PSB member | hendahanafi717@yahoo.fr |
| DELICE DANONE | Mohammed Ali Touzri | PSB member |  |
| ABSISKEY | Rémy M’Gadmi | Subcontractor WP8 | r.mgadmi@absiskey.com |
| PRIMA-IS | Mohamed Wageih | Invitee | mohamed.wageih@prima-med.org |

Phone call procedure: Microsoft Teams

The meeting will be recorded. Participation to the meeting implies acceptance to be recorded. Records will be available at the end of each section in the discussion/tchat.

- link to access the MilkQua Steering board meetings on June 3rd  Join Teams Meeting on June 3rd

- link to access the MilkQua Steering board meetings on June 4th  Join Teams Meeting on June 4th

Draft Agenda

Day 1 – afternoon

| 14.00 | Welcome, agenda determination |
| --- | --- |
| 14.05 | Participants round table |
| 14.15 | Short overview of the project updates WP1 – Coordination and management, by Latifa Najar, Idele State of implementation Discussion with Mohamed Wageih, project officer of PRIMA-IS Potential delays due to COVID-19 Discussion |
| 14.45 | Work Package presentations by WP leaders and discussion/consultation - 30 minutes per WP |
| 14.45 | WP2 - Innovative QMP practices in Tunisia Bénédicte Fusai and Philippe Roussel, Idele - France Introduction to First year activities and outcomes: - Report from stakeholders meetings and activities in Tunisia - Survey on main strains in mastitis Expected activities and outcomes for the Second year Discussion |
| 15.15 | WP3 – In vitro evaluation of bioactive molecules and extracts David Pereira, UPFF – Portugal Introduction to the scientific approach Activities and outcomes for first and second years Discussion |
| 15.45 | Short break |
| 16.00 | WP4 – In vivo evaluation of bioactive molecules and extracts Sonia Andres, CSIC – Spain Introduction to the scientific approach Activities and outcomes for first and second years Short presentation of Ralph Nehme’s (PhD) background Discussion |
| 16.30 | Discussion about Work Packages interactions and scientific approach |
| 16.30 | Moderation by Latifa Najar, Idele With all project partners Discussion |
| 17.00 | End of the first day |

Day 2 – afternoon

| 14.00 | Work Package presentations by WP leaders and discussion/consultation |
| --- | --- |
| 14.00 | WP5 – System biology assessment of the effects of essential oils after in vitro and in vivo studies – 20 minutes Fabrizio Ceciliani, UMIL – Italy Introduction to the Scientific approach Discussion |
| 14.20 | WP6 – Milk and dairy products processing and consumer studies – 20 minutes Saïd Bouhallab, INRAE – France Introduction to the Scientific approach Discussion |
| 14.40 | WP7 – Consumer assessment of milk - 20 minutes Raja SERAIRI, LPAM (CBBC) – Tunisia Introduction to the Scientific approach Discussion |
| 15.00 | WP8 - Communication and dissemination – 30 minutes Florence Macherez, Idele – France Rémy M’Gadmi, Absiskey Presentation of the communication and dissemination roadmap (tools, targets, events…) Guided discussion with participants: - How to improve communication and dissemination, enrich the website and social media? - How to develop specific communication into Arabic and French towards advisors, technicians, farmers, companies? |
| 15.30 | Short Break |
| 15.45 | Conclusion, decisions WP1 – Coordination and management Summary of decisions Preparation of End of first reporting period (M18 in Oct. 2020) Latifa Najar, Florence Macherez Idele |
| 16.30 | Closure |

Table of deliverables and milestones of the first and second years

| WP | Deliverable |  | Partner | Year 1 |  |  |  |  | Year 2 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | M1 Apr-19 | M3 June-19 | M9 Jan-20 | M10 Feb-20 | M12 Apr-20 | M15 Jul-20 | M18 Oct-20 | M20 Dec-20 | M23 Mar-21 | M24 Apr-21 |
| WP1 | D1.1 | Management committee constitution (MC) | IDELE |  |  |  |  |  |  |  |  |  |  |
| WP1 | D1.2 | Financial and administrative report | IDELE |  |  |  |  |  |  |  |  |  | I |
| WP2 | D2.1 | Evaluation and epidemilogy reports | OEP |  |  |  |  |  |  |  |  |  | I |
| WP2 | D2.2 | Milk quality improvement report | OEP |  |  |  |  |  |  |  |  |  | I |
| WP3 | D3.1 | Sampling/extraction protocol and list of plants | LPAM |  |  |  |  |  |  |  |  |  |  |
| WP3 | D3.2 | Bioactive extracts for subsequent biological assessment | LPAM |  |  | I |  |  |  |  |  |  |  |
| WP3 | D3.3 | Phytochemical profile of selected samples | LPAM |  |  | I |  |  |  |  |  |  |  |
| WP3 | D3.4 | Report on effects of plants/ essential oils on ruminal fermentation parameters & environmental impact | CSIC |  |  |  |  | I |  |  |  |  |  |
| WP3 | D3.5 | Report on the anti-inflammatory, antimicrobial & immunomodulatory properties of selected plant species | UPFF |  |  |  |  |  |  | I |  |  |  |
| WP3 | D3.6 | Safety report on selected samples | UPFF |  |  |  |  |  | I |  |  |  |  |
| WP4 | D4.1 | Protocols and data collection | CSIC |  |  |  | I |  |  |  |  |  |  |
| WP | Deliverable |  | Partner | Year 1 |  |  |  |  | Year 2 |  |  |  |  |
|  |  |  |  | M1 Apr-19 | M3 June-19 | M9 Jan-20 | M10 Feb-20 | M12 Apr-20 | M15 Jul-20 | M18 Oct-20 | M20 Dec-20 | M23 Mar-21 | M24 Apr-21 |
| WP4 | D4.2 | Report on EOs newborn calves and feed efficiency | CSIC |  |  |  |  |  |  |  |  |  | I |
| WP4 | D4.3 | Report on EOs newborn fed calves and health status | CSIC |  |  |  |  |  |  |  |  |  | I |
| WP4 | D4.4 | Report on the effect of EOs fed on milk yield, quality and health in adult cows | CSIC |  |  |  |  |  |  |  |  |  | I |
| WP6 | D6.3 | Antimicrobial activity of encapsulated Eos | LPAM |  |  |  |  |  |  |  |  |  | I |
| WP7 | D7.1 | Sensorial properties of milk enriched with encapsulated Eos | LPAM |  |  |  |  |  |  | I |  |  |  |
| WP7 | D7.2 | Questionnaire establishment on milk consumption | LPAM |  |  |  |  |  |  |  | I |  |  |
| WP7 | D7.3 | Validation of the questionnaire | LPAM |  |  |  |  |  |  |  |  | I |  |
| WP8 | D8.1 | Communication and dissemination materials | IDELE |  |  |  |  | I |  |  |  |  | I |
| WP8 | D8.2 | Plans for dissemination and exploitation of the results | IDELE |  |  |  |  | I |  |  |  |  | I |
| WP8 | D8.3 | Completed and planned communication activities | IDELE |  |  |  |  | I |  |  |  |  | I |